## Sheet1
Team member | Date | Data Collection & Processing | Model Building | Model Evaluation | Interface Building | Others
Islam, MdMaminur | 2018-10-24 | We started working on Ames Housing dataset. If we directly apply Multiple Linear Regression on the dataset, the performance might not be good. Hence, we cluster the data first and then apply Multiple Linear Regression on each cluster. But we can not apply k-means or other clustering algorithm on this dataset as our dataset contains both numerical and categorical data. We didn't find any framework for clustering which directly work on mixed data. Some preprocessing required here. Hence, we splitted our task into two parts. I implement a class which exposes appropriate functionalities to perform the preprocessing on the data. I'm still working on it.
Rahman, MD Lutfar | 2018-10-24 | As already mentioned by my partner, we need to do some preprocessing before we actually can do some Linear Regression. My partner is taking care of the primary preprpocessing. I am working on implementing a class for the preprocessed data for clustering. We are still working on it and trying to figure things out.
Islam, MdMaminur | 2018-10-31 | Since linear regression model can not work on categorical data, I converted categorial data into numerical data. For each category, I created a new variable and the variable is set to 1 if the category is true for a particular field otherwise the value is set to 0. Hence, the preprossing of the data is done by me and I exposed an interface so that my partner can access that preprocessed data
Rahman, MD Lutfar | 2018-10-31 |  | Our data contains 80 columns. After converting categorical data into numerical data, the number of columns increased a lot. We don't have that much data to train the model. Hence, our model may suffer from underfitting. So, I selectively wanted to choose some columns which best fit to our model. I created a regression model which runs on a combination of columns and in each iteration, I selected 3 columns that best fit to our model and next iterations is run on the remaining available columns. I continued as long as the score of the model score improves.
Islam, MdMaminur | 2018-11-07 |  |  | I evaluated the model with on selective columns using 10 folds cross validation and compared with 10 folds cross validation result for all columns. I noticed that there is no significant improve on score. I also tried to evaluate our model based on logistic regression. But logistic regression is too slow that it can not complete.
Rahman, MD Lutfar | 2018-11-07 |  |  |  | I am developing some services through which I can get the model evaluated data for our model. Later, I have plan to load the dash using D3 visualization tool which is a JavaScript library. I'm still working on that.